## BurndownChart
Sprint Tasks (Sprint Backlog) | Week 1 Oct. 20 - 26 | Week 2 Oct. 27 - Nov. 2 | Week 3 Nov. 3 - 9 | Week 4 Nov. 10 - 17 | Week 5 Nov. 17 - 24
Task 1 Student Register UI and Controller | 0 | 0 | 0 | 2 | 0
Task 1 Student Login UI and Controller | 0 | 0 | 0 | 4 | 0
Task 1 Student Main UI and Controller | 0 | 0 | 0 | 4 | 0
Task 1 Student Exam UI and Controller | 0 | 0 | 0 | 12 | 0
Task 1 Student Grade Statistics UI and Controller | 0 | 0 | 0 | 2 | 2
Task 1 Junit Tests for Implemented Tasks & Debugging | 0 | 0 | 0 | 0 | 4
Task 1 Debugging | 0 | 0 | 0 | 2 | 2
Task 1 Writing Supplementary Documents | 0 | 0 | 0 | 0 | 4
Task 2 make entities (Record, Question) | 0 | 0 | 2 | 0 | 0
Task 2 set up database | 0 | 0 | 1 | 0 | 0
Task 2 Teacher Login UI & Registration Controller | 0 | 1 | 2 | 0 | 0
Task 2 Teacher Question Bank UI & Controller | 0 | 2 | 4 | 2 | 0
Task 2 Teacher Exam Management UI & Controller | 0 | 2 | 5 | 4 | 0
Task 2 Writing Supplementary Documents | 0 | 0 | 0 | 2 | 2
Task 2 Junit Tests for Implemented Tasks & Debugging | 0 | 0 | 0 | 0 | 10
Task 3 make entities (Course,Exam,Grade,Manager,Student,Teacher) | 0 | 1 | 0 | 0 | 0
Task 3 Set up database Service | 0 | 0.5 | 0 | 0 | 0
Task 3 Manager Login UI & Controller | 0 | 1 | 0 | 0 | 0
Task 3 Teacher Grade Statistics UI & Controller | 0 | 0 | 2 | 0 | 0
Task 3 Manager Manage Student UI & Controller | 0 | 0 | 2 | 0 | 0
Task 3 Manager Manage Course UI & Controller | 0 | 0 | 2 | 0 | 0
Task 3 Manager Manage Teacher UI & Controller | 0 | 0 | 2 | 0 | 0
Task 3 Manager Manage Course Registration UI & Controller | 0 | 0 | 2 | 0 | 0
Task 3Junit Tests for Implemented Tasks & Debugging | 0 | 0 | 0 | 10 | 8
Task 3 Writing Supplementary Documents | 0 | 0 | 0 | 2 | 4
Total hours | 0 | 7.5 | 24 | 46 | 36

## GanttChart
GANTT CHART TEMPLATE
[7 empty] | Oct | [11 empty] | Nov
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE
[7 empty] | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Task 1
| Task 1 Login UI and Controller | 2024-11-12 | 2024-11-14 | 3 | Lee Hyunjin | 100% | bar: 12 to 14
| Task 1 Register UI and Controller | 2024-11-12 | 2024-11-14 | 3 | Lee Hyunjin | 100% | bar: 12 to 14
| Task 1 Main UI and Controller | 2024-11-14 | 2024-11-17 | 4 | Lee Hyunjin | 100% | bar: 14 to 17
| Task 1 Exam UI and Controller | 2024-11-15 | 2024-11-17 | 3 | Lee Hyunjin | 100% | bar: 15 to 17
| Task 1 Grade Statistics UI and Controller | 2024-11-16 | 2024-11-18 | 3 | Lee Hyunjin | 100% | bar: 16 to 17
| Task 1 Supplementary Documents | 2024-11-20 | 2024-11-20 | 1 | Lee Hyunjin | 100% | bar: 20
| Task 1 Debugging | 2024-11-18 | 2024-11-24 | 7 | Lee Hyunjin | 100% | bar: 18 to 24
| Task 1 Junit Tests for Implemented Tasks and Debugging | 2024-11-22 | 2024-11-24 | 3 | Lee Hyunjin | 100% | bar: 22 to 24
Task 2
| Task 2 make entities (Record, Question) | 2024-11-06 | 2024-11-09 | 4 | Seokhyeon Hong | 100% | bar: 6 to 9
| Task 2 set up database | 2024-11-06 | 2024-11-09 | 4 | Seokhyeon Hong | 100% | bar: 6 to 9
| Task 2 Teacher Login UI & Registration Controller | 2024-11-01 | 2024-11-06 | 5 | Seokhyeon Hong | 100% | bar: 1 to 6
| Task 2 Teacher Question Bank UI & Controller | 2024-11-01 | 2024-11-12 | 12 | Seokhyeon Hong | 100% | bar: 1 to 12
| Task 2 Teacher Exam Management UI & Controller | 2024-11-01 | 2024-11-12 | 12 | Seokhyeon Hong | 100% | bar: 1 to 12
| Task 2 Writing Supplementary Documents | 2024-11-12 | 2024-11-24 | 13 | Seokhyeon Hong | 100% | bar: 12 to 24
| Task 2 Junit Tests for Implemented Tasks & Debugging | 2024-11-12 | 2024-11-24 | 13 | Seokhyeon Hong | 100% | bar: 12 to 24
Task 3
| Task 3 make entities (Course,Exam,Grade,Manager,Student,Teacher) | 2024-11-04 | 2024-11-09 | 5 | Wong Hon Yin | 100% | bar: 4 to 9
| Task 3 Set up database Service | 2024-11-04 | 2024-11-05 | 1 | Wong Hon Yin | 100% | bar: 4 to 5
| Task 3 Manager Login UI & Controller | 2024-11-03 | 2024-11-04 | 1 | Wong Hon Yin | 100% | bar: 3 to 4
| Task 3 Teacher Grade Statistics UI & Controller | 2024-11-06 | 2024-11-09 | 3 | Wong Hon Yin | 100% | bar: 6 to 9
| Task 3 Manager Manage Student UI & Controller | 2024-11-03 | 2024-11-06 | 3 | Wong Hon Yin | 100% | bar: 3 to 5
| Task 3 Manager Manage Course UI & Controller | 2024-11-03 | 2024-11-06 | 3 | Wong Hon Yin | 100% | bar: 3 to 5
| Task 3 Manager Manage Teacher UI & Controller | 2024-11-03 | 2024-11-06 | 3 | Wong Hon Yin | 100% | bar: 3 to 5
| Task 3 Manager Manage Course Registration UI & Controller | 2024-11-10 | 2024-11-12 | 2 | Wong Hon Yin | 100% | bar: 10 to 12
| Task 3Junit Tests for Implemented Tasks & Debugging | 2024-11-09 | 2024-11-24 | 11 | Wong Hon Yin | 100% | bar: 9 to 24
| Task 3 Writing Supplementary Documents | 2024-11-09 | 2024-11-24 | 11 | Wong Hon Yin | 100% | bar: 9 to 24